## Slide 1
Day 3 — Morning
WS-1 Executable Blueprint
Build on Current Databricks / GCP
(Mexico & Wacam)
LA OSA Mexico & Wacam Harmonization Workshop
October 21, 2026 | 08:30 – 12:30
MATRIX-AI Technical Blueprint Workshop v07

## Slide 2
Session Objective & Context
WS-1: The Known Design Build
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
2 / 20
Produce the complete executable blueprint for Workstream 1
Starting Point
End-to-end pipeline is live in GCP for Mexico and Wacam, including existing KPIs and dashboards. Lingaro originally built this in GCP and now rebuilds it in Databricks.
Approach
Every CDRB section and every Day 2 pipeline block is mapped to named Lingaro resources, deliverables, and dates starting November 2. Six business-process tracks follow the same daily cadence.
Outcome
Working prototype in the Databricks exploration environment by end of December. Code migrates to Databricks on AWS once the new environment is ready — not the design.
Build Now, Migrate Later: The current Databricks/GCP environment is the sandbox where Lingaro demonstrates the design works end-to-end. Once the new Databricks on AWS is ready, the code migrates — not the design. This eliminates dead time and de-risks the AWS dependency.

## Slide 3
Fixed-Price SOW Commitment
[Draft] Blueprint Phase Context
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
3 / 20
⚠ FIXED-PRICE SOW COMMITMENT
During November and December 2026, Lingaro will execute the blueprint to design the global solution, following the executional steps agreed on Day 2 and applying all Code Design Review Board (CDRB) criteria (Sections A–L) to ensure proper design at every step.
As part of this phase, Lingaro must also deliver a working product running in the MDLZ Databricks exploration environment. Lingaro will establish federated connections with GCP and bring new data or manual files into this environment to build and prototype the solution.
This work is treated as fixed price. Lingaro must present the running prototype and results in January 2027. This is a non-negotiable SOW commitment.
WS-1 — Known Design Build: Based on OSA Mexico & Wacam (originally built by Lingaro in GCP), now rebuilt in the current Databricks/GCP sandbox.
WS-2 — Discovery & Reverse Engineering: Full end-to-end reverse engineering of GCP stored procedures and Power BI semantic models for Brazil and Southern Cone.

## Slide 4
The 6 Dedicated Business-Process Tracks
Each track follows the same steps and phases on a daily basis
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
4 / 20
1
OTC
Order-to-Cash: Sales orders, invoices, deliveries, order schedule & status
2
EPOS Sell-out / Channel Inventory
Point-of-sale data, channel inventory positions
3
SISO
Sell-in / Sell-out reconciliation, daily base, rules engine, customer chain assignments
4
Master Data, Historical & Manual Files
Hierarchies, ALT files, financial ratios, targets, SISO rules
5
Market Share
Nielsen-based calculations, resilient schema handling for schema changes
6
Gen BI Consumption Design
KPI architecture, metric view design, Genie setup including supervisor agents
▶ All 6 tracks run as parallel streams — each following the same daily execution steps aligned to the 8-block pipeline architecture from Day 2

## Slide 5
Track-to-Pipeline Block Mapping
Connecting business processes to Day 2's 8-block architecture
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
5 / 20
Business Track | B1 Ingestion | B2 Silver | B3 Core Domains | B4 Config | B5 KPI Calc | B6 Publish | B7 Metric Views | B8 Consump.
1 OTC | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤
2 EPOS / Ch. Inv. | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤
3 SISO | ○ | ○ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤
4 Master Data / Files | ⬤ | ⬤ | ⬤ | ⬤ | ○ | ○ | ○ | ○
5 Market Share | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤ | ⬤
6 Gen BI Consumption | ○ | ○ | ○ | ○ | ○ | ○ | ⬤ | ⬤
⬤ Primary scope ○ Supporting / derived scope
CDRB sections applicable per block: B1(A,I,K) | B2(B,D,E) | B3(A,B,E) | B4(C) | B5(A,D,E,F) | B6(F,G,J) | B7(I,K,L) | B8(I,L)

## Slide 6
November Deliverables Overview
WS-1 | Applicable CDRB: Sections A, C, D
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
6 / 20
7 DELIVERABLES | NOVEMBER 2026 | CDRB SECTIONS A · C · D
1
AS-IS to TO-BE pipeline design — use existing stored procedures as reference, then design TO-BE pipelines for Mexico and Wacam
CDRB: A
2
Manual files harmonization — populate new harmonized manual files with existing data from MX and WC
CDRB: C
3
Market Share optimization — review existing Nielsen ingestion; recommend resilient patterns for schema changes without pre-communication
CDRB: C
4
Business rules as configuration objects — AI-assisted extraction from existing GCP code to propose configurable objects
CDRB: C
5
Core Domain fit/gap analysis — against LA existing design, including Brazil for this case only
CDRB: A
6
KPI harmonization finalized — structure and material population with formulas, filters, and calculation (4-category approach)
CDRB: D
7
CDRB reviews register — show and apply reviews for Sections A01–A05, C01–C05, D01–D08 with planned actions
CDRB: A,C,D

## Slide 7
Nov Deliverable 1: AS-IS → TO-BE Pipeline Design
CDRB Section A — Architecture & Layering
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
7 / 20
Use existing GCP stored procedures as the starting reference, then design TO-BE pipelines following the 8-block architecture agreed on Day 2.
AS-IS (GCP Current State)
• Existing GCP stored procedures for MX & WC • Documented header in every procedure • Consistent exception handling with status logging • Deterministic hashed surrogate keys • Watermark-driven incremental processing • Narrow KPI model with unpivot (SISO) • Multi-calendar model (natural, MDLZ retail, O9) • SISO rules documented with BRD references
→
TO-BE (Databricks 8-Block Architecture)
• 8-block procedure template applied to every SP • Market as a parameter — zero code branches • 10 config tables + 8 shared functions • 6 canonical core domain entities (D1–D6) • KPI engine: calculate once, expand late • Generic 6-step publish layer • Unity Catalog metric views + Genie spaces • CDRB Sections A–L as quality gates
Every existing GCP procedure is mapped to its replacement in the new architecture. This is the foundation for the December build.

## Slide 8
Nov Deliverables 2 & 3: Manual Files & Market Share
CDRB Section C — Configuration: Business Rules as Data
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
8 / 20
② Manual Files Harmonization
Harmonize and populate the new harmonized manual files with existing data from MX and WC: • ALT hierarchies • SISO rules • Financial ratios • Targets Design the harmonized template that will later extend to full LA scope.
③ Market Share Optimization
Review existing Nielsen ingestion and provide recommendations for optimization: • Nielsen changes schema without pre-communication • Design resilient ingestion patterns • Schema detection and adaptive handling • Alerting when schema changes detected Ensures Market Share calculations remain trustworthy even when source formats shift.
Both deliverables map to CDRB Section C: every business rule exists as a versioned configuration row with owner and effective dates.

## Slide 9
Nov Deliverable 4: Business Rules as Config Objects
CDRB Section C — AI-Assisted Extraction from Existing Code
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
9 / 20
P2 Principle in Action: Rules as Data, Not Code
Business rules converted to configuration objects using AI to read existing GCP code and propose those objects. All 10 configuration tables populated from existing code.
1
Market scope definitions
2
Document type classifications
3
Reason code roles
4
Item category roles
5
Cut-off rules
6
Open order bucket conditions
7
FX conversion policies
8
SISO business rules
9
KPI registry (dictionary as executable metadata)
10
Quality rule thresholds
🤖 AI-Assisted: AI reads existing GCP stored procedures and proposes configuration objects. Engineers validate and refine. Same code for any market; only the configuration changes.

## Slide 10
Nov Deliverables 5 & 6: Core Domain Fit/Gap & KPI Harmonization
CDRB Sections A & D
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
10 / 20
⑤ Core Domain Fit/Gap Analysis
Analysis of current GCP domain structures against the 6 canonical entities from Day 2: D1 — Sales Orders D2 — Invoices D3 — Deliveries D4 — Order Schedule & Status D5 — Order–Invoice Detail D6 — Order–Delivery Detail Includes Brazil for this assessment only. Identifies what carries forward, what changes, and what is new.
⑥ KPI Harmonization — 4-Category Approach
A
Same name & formula → confirm and close
B
Same name, different formula → decide which definition wins
C
Different name, same intent → confirm canonical name
D
Unique to one BU → keep with justification or retire
Structure & material population: Formulas, filters, calculation logic, complete synonym register (legacy names → canonical names per BU)

## Slide 11
Nov Deliverable 7: CDRB Reviews Register
Sections A01–A05, C01–C05, D01–D08 — All Applicable Cases
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
11 / 20
Show and apply CDRB reviews and actions for all items related to November deliverables
Section A: Architecture & Layering
☐ A01 Each component does one job ☐ A02 Components are where they belong ☐ A03 Market is a setting, not code ☐ A04 Environment is a setting, not code ☐ A05 One conductor per layer
Section C: Configuration
☐ C01 Rules are rows, not code ☐ C02 No hidden numbers or dates ☐ C03 No copy-paste procedures ☐ C04 One source per reference dataset ☐ C05 Config changes are governed
Section D: Code Structure
☐ D01 8-block template followed ☐ D02 One logging method ☐ D03 Readable, focused transforms ☐ D04 Explicit missing data handling ☐ D05 Safe calculations ☐ D06 Consistent naming ☐ D07 Strict type checking ☐ D08 No ambiguous column selections
CDRB Operating Rhythm: Every PR for a TO-BE procedure, configuration table change, or shared function change. Review within 2 business days. Decisions: Approve | Approve with conditions | Redirect with rationale.

## Slide 12
December Deliverables Overview
WS-1 | Applicable CDRB: Sections B, E, F, G, H, I, J, K, L
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
12 / 20
8 DELIVERABLES | DECEMBER 2026 | CDRB SECTIONS B · E · F · G · H · I · J · K · L
1
Full solution design & sandbox build: base measures, loading/error handling, KPI engine, performance, scalability (H), security (I), testing (J), observability (K), documentation (L)
2
Foundations build: config tables, shared functions, utilities, SP template
3
Core domains design readiness and build into Databricks exploration zone
4
AI-assisted redesign: Market level objects for data preparation as configurable objects — optimization scenarios to avoid multiple steps and costs
5
AI-assisted redesign: Pre-calculated KPIs and data preparation — configurable objects for each step for future markets rollout
6
KPI domain E2E build for Wacam & Mexico: common design, pipelines, and configurable steps (8-step template)
7
Data Quality, Data Governance and Documentation end-to-end
8
CDRB reviews register: Sections B, E, F, G, H, I, J, K, L — all applicable cases listed with planned actions
December is the heaviest build month — solution design, foundations, core domains, KPI engine, and full quality governance.

## Slide 13
Dec Deliverable 1: Full Solution Design & Sandbox Build
CDRB Sections B, E, F, G, H, I, J, K, L
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
13 / 20
Full solution design finalization covering every engineering dimension:
Base Measures (F)
Calculate in base units (kg, local currency) only — publish layer handles expansion
Loading / Error Handling (E)
Merge-based loads, quality gates before persistence, all-or-nothing patterns
KPI Engine (F)
Parameterized calculation per domain, registry-driven composites, SISO rules engine
Performance (G)
Runtime budgets: ≤15 min per procedure, ≤2 hours full chain. Partitioning by market + date
Scalability (H)
Section H synthetic market test: fictional "ZZ" market added via config only — zero code changes
Security (I)
Least-privilege access, no credentials in code, RLS, audit columns on all tables
Testing Framework (J)
Unit tests for shared functions, golden-data tests, parallel-run reconciliation
Observability (K)
Complete run logs, automated alerts, operational runbooks, visible data lineage
Documentation (L)
Design note before build, time-bound waivers, registry-dictionary sync, legacy mapping
This comprehensive design enables the January 2027 prototype as a fixed-price SOW commitment.

## Slide 14
Dec Deliverables 2 & 3: Foundations & Core Domains Build
CDRB Sections B & E — Phase 1 & Phase 2 of the Build Sequence
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
14 / 20
② Foundations Build (Phase 1)
Configuration tables & shared utility functions
10 versioned market-keyed config tables
8 pure shared functions with unit tests
Stored-procedure template + unit test harness
8-block template: Contract → Context → Config → Extract → Transform → Quality Gate → Load → Log
Unity Catalog structure confirmed in current Databricks sandbox
③ Core Domains Build (Phase 2)
6 canonical domain entities built with the 8-block pipeline template: D1 — Sales Orders D2 — Invoices D3 — Deliveries D4 — Order Schedule & Status D5 — Order–Invoice Detail D6 — Order–Delivery Detail ✔ Quality gates passed ✔ CDRB Sections B & E reviewed and approved ✔ MX & WC ingestion running E2E in sandbox

## Slide 15
Dec Deliverables 4 & 5: AI-Assisted Redesign
CDRB Sections C & D — Configuration-Driven Data Preparation
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
15 / 20
④ Market-Level Objects Redesign
AI-assisted redesign of market-level objects for data preparation as configurable objects: • AI reads existing GCP code and proposes configurable alternatives • Provide optimization scenarios to avoid multiple steps and costs • Market-specific transformations become configuration rows • Every configuration object documented and version-controlled Enables: Zero code forks — every market difference resolved through configuration rows.
⑤ Pre-Calculated KPIs Redesign
AI-assisted redesign leveraging pre-calculated KPIs and data preparation: • Ensure configurable objects for each step • Future markets rollout readiness • Steps decomposed into testable, reusable units • Configuration-driven pipeline per KPI domain Enables: Adding a new market means adding configuration rows, not copying and rewriting the entire pipeline.
✔ Engineering Excellence: Pattern-first build discipline — one reference pipeline, one reference domain, one reference KPI — peer-reviewed and published as the mandated template before any variation is built. Variation handled by configuration: zero code forks.

## Slide 16
Dec Deliverable 6: KPI Domain Build E2E
Wacam & Mexico as a Common Design | CDRB Section F
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
16 / 20
KPI domain design readiness and build end-to-end following the repeatable 8-step template:
Register
1
▶
Configure
2
▶
Build
3
▶
Publish
4
▶
Parallel
Run
5
▶
Reconcile
6
▶
Quality
Gate
7
▶
Sign-off
8
KPI Domains Covered:
Sell-in Order/Invoice Roles & signs from config, open-order buckets, net-revenue ratio
Sell-in Delivery Delivered, on-time, not-invoiced, completed-standard measures
Sell-in Targets Quotas with configurable version rule
SISO Daily Base One daily grain; weekly/monthly by calendar service
SISO Rules Engine Priority-based matching, finite formula vocabulary
Inventory Stock snapshots, snapshot additivity (last value, not sum)
Shipment Shipment detail base measures
Market Share Nielsen-based calculations with resilient schema handling
Metric views and Genie spaces designed. AI/BI dashboards validated against source system baselines.

## Slide 17
Dec Deliverables 7 & 8: Quality, Governance & CDRB Reviews
CDRB Sections B, E, F, G, H, I, J, K, L
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
17 / 20
⑦ Data Quality, Governance & Documentation E2E
✔ Every pipeline layer has quality gates ✔ Data lineage is visible end-to-end ✔ KPI registry and dictionary always in sync ✔ Design note before build for all Tier 1 components ✔ All waivers explicit and time-bound ✔ Legacy decommission mapping maintained ✔ Operational runbooks published ✔ Automated alerts for failures and quality issues ✔ Complete run logs with status, rows, watermark, duration
⑧ CDRB Reviews Register — December
☐ Section B Core Domain Design (B01–B07) ☐ Section E Data Loading & Quality (E01–E05) ☐ Section F KPI Calculation & Accuracy (F01–F10) ☐ Section G Performance & Cost (G01–G07) ☐ Section H Scalability — synthetic market test (H01–H04) ☐ Section I Security & Compliance (I01–I04) ☐ Section J Testing & Reconciliation (J01–J04) ☐ Section K Observability & Operations (K01–K04) ☐ Section L Documentation & Governance (L01–L04)
Quality at Source: Data quality checks are embedded as the pipeline is built — not validated after the fact. Every deliverable is closed only when the corresponding CDRB section items are verified. The CDRB review register is updated weekly with all applicable items and planned actions per section.

## Slide 18
Three-Phase Build Sequence
Timeline, Deliverables, and CDRB Gates per Phase
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
18 / 20
Phase | Name | Timeline | Deliverables | CDRB Gates
1 | Foundations | Nov Wk 1–2 | • Configuration tables & shared utility functions • SP template + unit test harness • Unity Catalog structure confirmed | A, C, D
2 | Core Domains | Nov Wk 3 – Dec Wk 1 | • 6 canonical entities built with 8-block template • Quality gates passed; CDRB B & E reviewed • MX & WC ingestion running E2E in sandbox | B, E
3 | KPI Domains | Dec Wk 2–4 | • 8-step repeatable template per domain • All KPI domains complete with metric views & Genie • AI/BI dashboards validated against baselines | F, G, H, I, J, K, L
Phase 1: Foundations
▶
Phase 2: Core Domains
▶
Phase 3: KPI Domains
Each phase has a formal CDRB quality gate that must be passed before advancing to the next phase.

## Slide 19
CDRB Section-to-Month Mapping for WS-1
November & December Quality Gates
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
19 / 20
Sec. | Section Name | November | December | January
A | Architecture & Layering | ⬤ Primary | ○ Review | ○ Review
B | Core Domain Design | ○ Prep | ⬤ Primary | ○ Review
C | Configuration: Business Rules as Data | ⬤ Primary | ○ Review | ○ Review
D | Code Structure & Readability | ⬤ Primary | ○ Review | ○ Review
E | Data Loading & Quality Assurance | ○ Prep | ⬤ Primary | ○ Review
F | KPI Calculation, Rules & Accuracy | ○ Prep | ⬤ Primary | ⬤ Primary
G | Performance & Cost Efficiency | ― | ⬤ Primary | ○ Review
H | Scalability & Multi-Market Readiness | ― | ○ Prep | ⬤ Primary
I | Security & Compliance | ― | ⬤ Primary | ○ Review
J | Testing & Reconciliation | ― | ⬤ Primary | ○ Review
K | Observability & Operations | ― | ⬤ Primary | ○ Review
L | Documentation & Governance | ○ Prep | ⬤ Primary | ○ Review
⬤ Primary = primary quality gate ○ Review = ongoing review Prep = preparation activities ― = not yet active

## Slide 20
Expected Outcomes & Transition to WS-2
Closing WS-1 Morning Session
LA OSA 2.0 Blueprint Workshop | Day 3 Morning | WS-1: Mexico & Wacam
20 / 20
✔
Executable WS-1 plan with named Lingaro resources assigned to each business-process track
✔
Clear daily cadence with same steps and phases applied to each of the 6 tracks
✔
CDRB review register populated with all applicable items and planned actions per month
✔
Working prototype foundations in the Databricks exploration zone by end of December
✔
January delivery commitment confirmed as part of fixed-price SOW
▶ Afternoon Session: WS-2 Executable Blueprint
Workstream 2 builds the parallel plan for Brazil & Southern Cone — 8 business-process tracks (including Brazil PVC/VR and Snacksync), back-office/front-office team split, market visits (São Paulo, Buenos Aires), and full LA harmonization deliverables for November and December.